## Read Me
BP Connect CRM — Mobile Test Matrix
Generated | 2026-07-30 · app v1.2.0 (versionCode 4) · backend api.bpconnect.app
How to use | Work through the Test Matrix sheet. Set Status per case; put build + date in 'Tested on'; note anomalies in Notes.
Env column
Emulator | Runnable on the Android emulator (or RN-web where noted). Agents can run these.
Device | Needs real hardware — camera/ML Kit OCR, biometrics, SIM SMS, install/update loop (HUMAN-QUEUE §5, fleet Galaxy A15).
Any | Backend-observable; device irrelevant.
Priority | P1 = must pass before fleet rollout · P2 = should pass · P3 = nice to verify
Status values | Pass / Fail / Blocked / N/A / Untested
Automated coverage | Existing gates already covering the case: mobile Jest (35), Playwright RN-web happy path, api pytest (51). '—' = manual-only.
Known gates | Debug-keystore signing (HUMAN-QUEUE §2) · Semaphore server-SMS blocked on sender name (§3) · single shared tenant — clean up e2e data.

## Test Matrix
ID | Area | Feature | Test Case | Steps | Expected Result | Env | Priority | Automated Coverage | Status | Tested On (build/date) | Notes
UPD-01 | Update & Distribution | First install | Fresh install from public URL | On a device with no app, browse to https://apk.bpconnect.app/bpconnect-crm-latest.apk, download, install via OS installer | APK installs (unknown-sources prompt accepted); app launches to Login | Device | P1 | — | Untested
UPD-02 | Update & Distribution | UpdateGate | No prompt when up to date | Launch v1.2.0 (versionCode 4) with network up | No update prompt; app proceeds normally | Emulator | P1 | — | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | No prompt; straight to Login with network up
UPD-03 | Update & Distribution | UpdateGate | Update prompt on older build | Launch v2/v3 build while update.json advertises versionCode 4 | Prompt appears with release notes; Download → sha256 verified → OS installer opens | Device | P1 | — | Untested
UPD-04 | Update & Distribution | UpdateGate | Corrupt/failed download handling | Interrupt the APK download (airplane mode mid-download) | Clear error, no crash; retry possible; no half-installed state | Device | P2 | — | Untested
UPD-05 | Update & Distribution | UpdateGate | Offline launch | Launch app with no network | Update check fails silently (no block); app usable to login screen; API errors surfaced gracefully | Emulator | P2 | — | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | DNS-dead + wifi-off launches: silent update-check fail, app usable, clean error states
AUTH-01 | Auth | Register | Client-side validation | Submit empty form; bad email; short password; mismatched confirm password | Inline field errors; no network call until valid | Emulator | P1 | Jest + Playwright happy-path | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Required name / invalid email / short password / mismatch all inline
AUTH-02 | Auth | Register | Successful registration | Fill valid name/email/password/confirm → Create Account | POST /auth/register 200; lands on Dashboard | Emulator | P1 | Playwright happy-path; api pytest | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Register -> Dashboard
AUTH-03 | Auth | Register | Duplicate email rejected | Register with an email that already exists | Server error surfaced in UI; no crash; stays on Register | Emulator | P2 | api pytest | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | "account with this email already exists" shown, stays on Register
AUTH-04 | Auth | Login | Wrong password | Login with valid email + wrong password | Error message; no session stored | Emulator | P1 | api pytest | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | "invalid credentials", stays on Login
AUTH-05 | Auth | Login | Successful login | Login with valid credentials | Lands on Dashboard with live data | Emulator | P1 | Playwright (register path) | Pass | v1.2.0 (vc4) emulator · 2026-07-30
AUTH-06 | Auth | Session | Cold-start session restore | Login, force-stop app, relaunch | Session restored from SecureStore; Dashboard without re-login | Emulator | P1 | Jest (session store) | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Force-stop -> relaunch -> Dashboard without re-login
AUTH-07 | Auth | Session | Token refresh under concurrency | Leave app until access token expires; trigger several API calls at once (e.g. Dashboard focus) | Single-flight refresh; no logout, no replay-detection revocation | Emulator | P2 | Jest (single-flight refresh) | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Access TTL 15m; expired-token cold load + focus refetch refreshed silently, no logout/revocation
AUTH-08 | Auth | Biometrics | Biometric consent + unlock | Enable biometrics on consent screen; relaunch; unlock with fingerprint/face | Stored session pair unlocked (incl. refresh token); Dashboard loads | Device | P1 | Jest (empty-refresh-token regression) | Untested
AUTH-09 | Auth | Password reset | Reset request email | POST reset from Login → check inbox | 200; Resend email delivered with working reset flow | Any | P2 | api pytest; live-verified 2026-07-28 | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Per 2026-07-28 live verification (Resend); not re-run
DASH-01 | Dashboard | Tiles | Live totals | Login with data present | Contact totals, activeDealsCount, pipelineValue match GET /dashboard; reminder shown | Emulator | P1 | api pytest (dashboard) | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | 29 contacts / 3 active deals / P75,001 matched GET /dashboard
DASH-02 | Dashboard | Navigation | Deal tile links to Pipeline | Tap active-deals / pipeline-value tile | Pipeline board opens on relevant view | Emulator | P2 | Jest 35/35 (PR #61) | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Active-deals tile opens Pipeline
DASH-03 | Dashboard | Refresh | Focus refetch | Change data elsewhere (e.g. save contact), navigate back to Dashboard | Numbers update without manual refresh | Emulator | P2 | — | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Nav-focus refetch works. Note: resume-from-background does NOT refetch (only nav focus / cold start)
CON-01 | Contacts | List | Server search | Type in search box | GET /contacts?q= results; debounced; empty state when no match | Emulator | P1 | api pytest (q=) | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Debounced server search; count badge; 0-match handled
CON-02 | Contacts | List | Filter / sort / pagination | Apply status filter, change sort, scroll past first page | Server-side filter+sort respected; next page loads seamlessly | Emulator | P1 | api pytest | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Filter + pagination (29 rows across 2 pages) pass. NO sort control exposed in UI - top-right icon is Import/Export
CON-03 | Contacts | List | Optimistic favorite toggle | Tap star on a row; then again | Instant UI flip; server revision returned; reverts on API failure | Emulator | P2 | Jest; live-verified PATCH revision | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Optimistic star; server favorite=true revision=1
CON-04 | Contacts | List | Loading / error / empty states | Fresh load; airplane mode; empty account | Spinner → content; readable error + retry; friendly empty state | Emulator | P2 | Jest | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Spinner, offline error+retry, empty state all seen
CD-01 | Contact Detail | View | Full contact render | Open a saved contact | All fields, completeness score, card image (if uploaded), activity timeline | Emulator | P1 | Playwright happy-path (view) | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Full render incl. quick actions, CRM details, deal card, timeline
CD-02 | Contact Detail | Edit | Revision-aware PATCH | Edit a field, save | PATCH succeeds; revision increments; UI reflects server state | Emulator | P1 | api pytest; live-verified | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | PATCH ok, revision 0->1
CD-03 | Contact Detail | Edit | 409 conflict handling | Edit the same contact from two sessions; save the stale one | 409 surfaced with reload/merge path; no silent overwrite | Emulator | P2 | api pytest (409) | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Stale save -> "Contact changed elsewhere - reloaded", no overwrite
CD-04 | Contact Detail | Activity | Activity composer | Add a note/activity from the composer | POST activity 201; appears at top of timeline | Emulator | P1 | api pytest | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Note 201, top of timeline
SCAN-01 | Card Scanner | Permissions | Camera permission flow | Dashboard → Scan a Business Card → Allow Access | Permission prompt; grant → live camera; deny → 'Import from Photos' fallback banner | Emulator | P1 | Playwright (deny path) | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | OS deny -> Import-from-Photos fallback banner; grant -> live camera with frame overlay
SCAN-02 | Card Scanner | OCR | Live camera scan → ML Kit OCR | Point camera at a real business card | Text extracted on-device; fields prefilled on Review screen | Device | P1 | — (mock OCR on web/emulated camera) | Untested
SCAN-03 | Card Scanner | OCR | Photo import → OCR | Import a card photo from gallery | ML Kit extracts fields from the image; Review screen prefilled | Emulator | P1 | Playwright (mock path) | Blocked | v1.2.0 (vc4) emulator · 2026-07-30 | EMULATOR: ML Kit latin model is Play-delivered; GMS module download fails without Play sign-in. BUG: infinite "Analysing card..." - no timeout/error/manual fallback
SCAN-04 | Card Scanner | Review | Edit extracted fields | Correct a misread field on Review screen | Edits persist to the saved contact | Emulator | P2 | Playwright happy-path | Blocked | v1.2.0 (vc4) emulator · 2026-07-30 | Blocked by SCAN-03 (no OCR result on emulator)
SCAN-05 | Card Scanner | Duplicates | Duplicate-contact banner | Scan a card matching an existing contact | 'May already exist' banner; View Existing opens it; Save as New creates a second record | Emulator | P2 | Playwright (both states handled) | Blocked | v1.2.0 (vc4) emulator · 2026-07-30 | Blocked by SCAN-03
SCAN-06 | Card Scanner | Details | Required marketing consent | Try to save without answering Marketing Consent | Save blocked until Yes/No chosen (testID marketing-consent-*) | Emulator | P1 | Playwright happy-path | Blocked | v1.2.0 (vc4) emulator · 2026-07-30 | Blocked by SCAN-03
SCAN-07 | Card Scanner | Save | Save → POST /contacts | Complete details → Save Contact | 201; Confirm screen names contact; View Contact shows live GET /contacts/{id} | Emulator | P1 | Playwright happy-path; api pytest | Blocked | v1.2.0 (vc4) emulator · 2026-07-30 | Blocked by SCAN-03
SCAN-08 | Card Scanner | Card image | R2 upload opt-in + temp cleanup | Save with card-image upload enabled | Presign → PUT to R2 → public URL 200 on contact; local temp file deleted | Emulator | P2 | api pytest (cards); live-verified presign | Blocked | v1.2.0 (vc4) emulator · 2026-07-30 | Blocked by SCAN-03; presign->PUT->public 200 live-verified via API 2026-07-29
DEAL-01 | Deals | Start | Start Deal from contact | Contact Detail → Start a Deal → title + value (₱) → Start Deal | POST /deals; deal card appears; 'Deal started' on timeline; dashboard tiles update | Emulator | P1 | Jest (PR #60); api pytest 51/51 | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Deal card + "Deal started" timeline event + dashboard tiles
DEAL-02 | Deals | Input | Peso value parsing incl. comma decimals | Enter values like 75,000 / 75000.50 / 75.000,50 | Parsed correctly per fix in PR #62 review; no NaN or silent truncation | Emulator | P2 | Jest (comma-decimal fix) | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | "75,000.50" parsed to 75000.5 server-side
DEAL-03 | Deals | Advance | Server-driven stage buttons | Open a deal; observe advance/lost buttons | Buttons render ONLY from server allowedTransitions (no client stage graph) | Emulator | P1 | Jest; api pytest | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Buttons render exactly from server allowedTransitions
DEAL-04 | Deals | Advance | Legal advance | Advance lead → qualified | POST /deals/{id}/advance 200; stage event on timeline ('Lead → Qualified') | Emulator | P1 | api pytest; live e2e 2026-07-29 | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | "Lead -> Qualified" timeline event; buttons update
DEAL-05 | Deals | Advance | Illegal transition blocked | Attempt a jump the server disallows (e.g. qualified → won) | 409 with allowedTransitions; UI shows valid options only; no state corruption | Emulator | P1 | api pytest (409 + allowed) | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | API 409 + allowedTransitions; UI never offers illegal jump
DEAL-06 | Deals | Lost | Mark Deal Lost | Tap lost action → confirm 'Mark Deal Lost?' | Deal moves to lost; board + dashboard reflect it | Emulator | P2 | Jest | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Confirm dialog -> lost/completed; board + dashboard reflect
DEAL-07 | Deals | Error path | No duplicate deal on failed create | Force a failed POST /deals (airplane mode), retry | Single deal after retry (duplicate-on-error fix, PR #62 review) | Emulator | P2 | Jest (regression) | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Offline create fails w/o phantom deal; retry -> exactly 1
PIPE-01 | Pipeline | Board | Stage columns rollup | Open Pipeline board with deals in several stages | Counts + ₱ totals per stage match GET /pipeline | Emulator | P1 | api pytest (board) | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | P75,001 / 3 open / 0-1 won-lost; per-stage counts match
PIPE-02 | Pipeline | Board | Post-advance repaint on correct tab | Advance a deal from the board | Deal moves to the new stage's tab; no wrong-tab repaint (PR #62 fix) | Emulator | P2 | Jest (regression) | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Advance from board repaints on same tab correctly
PIPE-03 | Pipeline | Empty | Empty stage messaging | View a stage with no deals | 'Start deals from a contact's page' empty state | Emulator | P3 | — | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Empty-stage message present
QA-01 | Quick Actions | Call | Dial + auto-log | Contact Detail → call action → return to app | Dialer opens with contact number; auto-log prompt; activity logged on confirm | Device | P1 | Jest (PR #62) | Untested
QA-02 | Quick Actions | Email | Mail + auto-log | Tap email quick action → return | Mail composer with contact address; auto-log prompt works | Emulator | P2 | Jest | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Gmail intent + "Log this email?" banner -> email activity logged
QA-03 | Quick Actions | SMS | SMS via device SIM + auto-log | Tap SMS quick action; send a text | SMS app opens with number; auto-log on return (unaffected by Semaphore gate) | Device | P2 | — | Untested
REM-01 | Reminders | Permission | Notification permission request | Trigger first follow-up scheduling | OS permission prompt; denial handled gracefully (no crash, feature no-ops) | Emulator | P1 | Jest | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | OS prompt on first schedule; denial degrades silently, save unaffected
REM-02 | Reminders | Scheduling | Follow-up reminder fires | Schedule a follow-up a few minutes out; background the app | Local notification fires at the scheduled time; tap opens the contact | Device | P1 | Jest (scheduling logic) | Untested
REM-03 | Reminders | Foreground | Reminder while app open | Let a reminder fire with app foregrounded | Foreground handler shows it (PR #62 fix); no silent drop | Emulator | P2 | Jest (regression) | Blocked | v1.2.0 (vc4) emulator · 2026-07-30 | SUSPECT BUG: no scheduled notification ever registered (no expo store, no alarm) even after grant + date change. Verify REM-02/03 on device carefully
IE-01 | Import/Export | Export | CSV export round-trip | Export contacts to CSV | File contains all contacts; formula-injection-safe cells (=,+,-,@ prefixed) | Emulator | P2 | api pytest; library #258 fix | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | 27 rows; formula cells escaped ('=2+5, '@cmd¦test)
IE-02 | Import/Export | Import | Preview → map → import | Pick a CSV; review preview; adjust mapping; run import | State machine none→previewing→mapped→imported; correct row counts; errors listed | Emulator | P2 | api pytest; live round-trip verified | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Preview "2 rows / 5 columns mapped" -> 2 imported -> View Contacts
SEC-01 | Security | Transport | No cleartext traffic | Inspect release build / attempt http:// call | usesCleartextTraffic off; only https://api.bpconnect.app | Emulator | P1 | Static check (#49) | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | usesCleartextTraffic=false in installed manifest
SEC-02 | Security | Storage | Tokens in secure storage only | Inspect app storage after login | Session pair in SecureStore/Keystore; nothing sensitive in AsyncStorage or logs | Emulator | P1 | #51 review | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | No AsyncStorage DB; SecureStore encrypted; no raw JWT in app data or logcat
SEC-03 | Security | Build | R8-minified release boots | Install release APK; exercise all top-level screens | No ProGuard/R8 ClassNotFound crashes (ML Kit, expo modules survive shrink) | Emulator | P1 | Static verify done; runtime = this matrix | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | R8 build exercised across all top-level screens, no ClassNotFound crashes
NF-01 | Non-functional | Performance | Cold start time | Force-stop; launch; time to interactive Login/Dashboard | ≤ ~4s on a fleet A15 (slower on emulator is OK) | Device | P3 | — | Untested
NF-02 | Non-functional | Resilience | Airplane-mode UX sweep | Toggle airplane mode on each main screen | Every screen shows readable error + retry; no crash, no infinite spinner | Emulator | P2 | — | Pass | v1.2.0 (vc4) emulator · 2026-07-30 | Dashboard offline: readable error + Try Again recovers; deal form offline: no crash, no dup